## Sheet1
Task | Start Date | Days to complete
UI design completion | 2024-04-25 | 10
Frontend Implementation | 2024-05-06 | 20
Database setup | 2024-05-27 | 10
Endpoints setup | 2024-06-07 | 7
Connection of frontend to backend | 2024-06-15 | 5
Training ML models | 2024-06-21 | 20